

**Revised Implementation Plan For Phase 1**

**(2018-2020)**

**Planning Visit:-**

Visit a: 17 September 2018 (Meeting with NCDOE), Term 3

Visit b: 6 – 9 November 2018, (Exploratory site visits to districts x2), Term 4

**Implementation of the BCP:-**

Visit 1: 4-9 February 2019 (colour and shape), Term 1\*

Visit 2: 6-10 May 2019 (size and position), Term 2\*

Visit 3: 22-26 July 2019 (support and mentoring), Term 3

 Visit 4: 19-24 August 2019 (number and letter), Term 3\*

Visit 5: 28-01 Oct/Nov 2019 (support and mentoring), Term 4

Visit 6: February/March 2020 (support and mentoring), Term 1

Visit 7: June/July 2020 (support and mentoring), Term 2

Visit 8: October/Nov 2020 (graduation ceremony and support), Term4

*\* Training Visits*

Gaps between visits:

Visit 1 – 2: 10 weeks (colour and shape is implemented)

Visit 2 - 3: 12 weeks (size is finished and position is initiated)

Visit 3 - 4: 5 weeks (position is finished and number-letter initiated)

Visit 4 – 5: 10 weeks (number-letter continued)

Visit 6 - 7: 12 weeks (colour, shape, and size is implemented)

Visit: 7 – 8: 12 weeks (position, number and letter is implemented)

Length of time spent per conceptual domain:

6 weeks for colour + 6 weeks for shape

6 weeks for size + 6 weeks for position

15 weeks for number and letter